## Sheet1
CHANGE REQUEST
Sr. No. | Screenshot/Request nos | Issue Description | Valid/Invalid | Severity | Issue raised on | Completion date | Status | Developer Comments
1 | 070420180012761 | When we click on Add new link Material and provide Material Code , then on Enter press , system goes back to previous page . | Valid | High | 2018-07-03 | 2018-07-06 | Done
2 |  | There is no values available for Drop-down fields ( Section & Field ) | Valid | High | 2018-07-03 | 2018-07-04 | Done
3 |  | Material description is not getting auto-populated. | Valid | Medium | 2018-07-03 |  |  | 04/07/18: As per discussion with Dilip Ram, Material description will be entered by User. There is no need for auto populate
4 |  | File Upload not working even when provided with the given format | Valid | Medium | 2018-07-04 | 2018-07-06 | Done
5 |  | At first Approver ( BFG ) , There are 2 buttons "Proceed to Submit " & " Approve ". Kindly clarify the diiference | Valid | Low | 2018-07-04
Material Extension
Sr. No. | Screenshot/Request nos | Issue Description | Valid/Invalid | Severity | Issue raised on | Completion date | Status | Developer Comments
1 |  | There is no Validation for mandatory Fields | Valid | high | 2018-07-03 | 2018-07-06 | Done
2 |  | Material Description is not getting auto-populated | Valid | Medium | 2018-07-03 |  |  | 04/07/18: As per discussion with Dilip Ram, Material description will be entered by User. There is no need for auto populate
3 |  | When we provide material code the below section becomes disabled , whereas if click on proceed to submit or SAVE , those fields will get enabled and mandatory |  |  | 2018-07-04
Block/Unblock
Sr. No. | Screenshot/Request nos | Issue Description | Valid/Invalid | Severity | Issue raised on | Completion date | Status | Developer Comments
1 |  | In Master block/unblock pop-up , there are no values present for plant drop-down field ( mandatory ) | Valid | High | 2018-07-04 | 2018-07-06 | Done