## AllProjects
ALL PROJECTS
Project Name | API Plant | Formulation Plant | Product Category | API Vendor | Brand Name | Innovator Brand Name | Read Date | ELD | API Procurement Start | API Procurement End | APIMSD - 0 | APIMED - 0 | FPMSD - 0 | FPMED - 0 | APIMSD - 1 | APIMED - 1 | FPMSD - 1 | FPMED - 1
Amlodipine 2,5 and 5 mg | LUPIN TARAPUR | GOA | REGULAR | NA | NA | NA | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
AMLODIPINE,VALSARTAN AND HCTZ TABS | OUTSOURCED, LUPIN TARAPUR | GOA | REGULAR | NA | NA | Exforge HCT | 01 Jan 2015 | 01 Jan 2015 | 18 Jul 2014 | 02 Oct 2014 | 08 Aug 2014 | 29 Oct 2014 | 08 Oct 2014 | 06 Dec 2014 | 28 Jul 2014 | 05 Nov 2014 | NA | NA
Amlodipine,Valsartan Tabs | LUPIN TARAPUR | GOA | REGULAR | NA | NA | Exforge | 01 Apr 2015 | 02 Apr 2015 | NA | NA | 06 Nov 2014 | 14 Feb 2015 | 26 Jan 2015 | 22 Mar 2015 | NA | NA | NA | NA
Atorvastatin Calcium Tabs | LUPIN DABASHA | GOA | REGULAR | NA | NA | NA | 11 Jul 2015 | 18 Nov 2015 | NA | NA | 02 Apr 2015 | 09 Aug 2015 | 14 Jul 2015 | 08 Nov 2015 | NA | NA | NA | NA
Azithromycin fOS | LUPIN DABASHA | GOA | CRITICAL | NA | NA | Zithromax | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
Azithromycin Tablets | LUPIN DABASHA | GOA | REGULAR | NA | NA | Zithromax | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
Bimatoprost Ophthalmic Solution 0,03 |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Bimatoprost Opthalmic Solution- 0,01percent | OUTSOURCED | INDORE OSD/OPTHAL | CRITICAL | CHIROGATE INTERNATIONAL INC | NA | Lumigan 0.01% | 02 Apr 2015 | 02 Apr 2015 | 16 Nov 2014 | 15 Jan 2015 | NA | NA | 21 Jan 2015 | 17 Mar 2015 | NA | NA | NA | NA
Bromfenac Ophthalmic Solution | OUTSOURCED | INDORE OSD/OPTHAL | NA | CHEM WERTH INC. USA | NA | Bromday | 02 Apr 2015 | 20 Jun 2015 | NA | NA | 29 Jan 2015 | 30 Mar 2015 | 04 Apr 2015 | 20 May 2015 | NA | NA | NA | NA
Brompheniramine Maleate,( GRx of Bromfed Suspension) | OUTSOURCED | AURANGABAD | REGULAR | SUPRIYA LIFESCIENE, AVON ORGANICS, DIVIS LAB | NA | Bromfed | 02 Apr 2015 | 20 Jun 2015 | NA | NA | 29 Jan 2015 | 30 Mar 2015 | 04 Apr 2015 | 20 May 2015 | NA | NA | NA | NA
Bupropion XL Tabs | OUTSOURCED | GOA | CRITICAL | HIKAL | NA | Wellbutrin XL | 01 Nov 2014 | 04 Jan 2015 | NA | NA | 30 Aug 2014 | 29 Oct 2014 | 03 Nov 2014 | 19 Dec 2014 | NA | NA | NA | NA
Calcium Acetate Caps | OUTSOURCED | GOA | REGULAR | KEMIRA | NA | Phoslo | 02 Apr 2015 | 20 Jun 2015 | NA | NA | 29 Jan 2015 | 30 Mar 2015 | 04 Apr 2015 | 20 May 2015 | NA | NA | NA | NA
Carvedilol CR Caps | LUPIN TARAPUR | GOA | CRITICAL | NA | NA | Coreg CR | 01 May 2015 | 04 Jun 2015 | NA | NA | 12 Feb 2015 | 15 May 2015 | 04 May 2015 | 07 Jun 2015 | NA | NA | NA | NA
Celecoxib Caps (AUS) | LUPIN TARAPUR | GOA | CRITICAL | NA | NA | Celebrex | 30 Apr 2014 | 01 Apr 2015 | NA | NA | 10 Apr 2014 | 06 Dec 2014 | 17 Dec 2014 | 20 Feb 2015 | NA | NA | NA | NA
Celecoxib Capsules | LUPIN TARAPUR | GOA | CRITICAL | NA | NA | Celebrex | 02 Apr 2015 | 02 Apr 2015 | NA | NA | 06 Nov 2014 | 14 Feb 2015 | 26 Jan 2015 | 22 Mar 2015 | NA | NA | NA | NA
Clarithromycin ER Tabs | NA | GOA | REGULAR | NA | NA | NA | 02 Apr 2015 | 20 Jun 2015 | NA | NA | 29 Jan 2015 | 30 Mar 2015 | 04 Apr 2015 | 20 May 2015 | NA | NA | NA | NA
Colesevelam HCl Tabs | OUTSOURCED | GOA | CRITICAL | FARMOSA | NA | Welchol | 02 Apr 2015 | 02 Apr 2015 | 16 Nov 2014 | 15 Jan 2015 | NA | NA | 21 Jan 2015 | 17 Mar 2015 | NA | NA | NA | NA
Colesevelam Hydrochloride Powder for Oral Suspension | LUPIN TARAPUR | GOA | CRITICAL | NA | NA | Welchol | 02 Apr 2015 | 02 Apr 2015 | NA | NA | 06 Nov 2014 | 14 Feb 2015 | 26 Jan 2015 | 22 Mar 2015 | NA | NA | NA | NA
DESVENLAFAXINE ER TABS (AUS) | LUPIN TARAPUR | GOA | CRITICAL | NA | NA | Pristiq | 01 Dec 2014 | 01 Mar 2015 | NA | NA | 15 Oct 2014 | 25 Nov 2014 | 01 Dec 2014 | 01 Feb 2015 | NA | NA | NA | NA
Desvenlafaxine Succinate ER Tabs | LUPIN DABASHA | GOA | REGULAR | LUPIN DABASHA | Pristiq | Pristiq | 02 Apr 2015 | 02 Apr 2015 | NA | NA | 06 Nov 2014 | 14 Feb 2015 | 26 Jan 2015 | 22 Mar 2015 | NA | NA | NA | NA
Diclofenac Sodium Topical Solution | OUTSOURCED | INDORE OSD/OPTHAL | REGULAR | AMOLI ORGANICS PVT. LTD. | NA | Pennsaid | 02 Apr 2015 | 20 Jun 2015 | NA | NA | 29 Jan 2015 | 30 Mar 2015 | 04 Apr 2015 | 20 May 2015 | NA | NA | NA | NA
Donepezil SR Tabs (23mg) | OUTSOURCED | GOA | REGULAR | HETERO | NA | Aricept | 01 Sep 2014 | 11 Sep 2014 | NA | NA | 01 Nov 2013 | 31 Dec 2013 | 05 Jan 2014 | 20 Feb 2014 | NA | NA | NA | NA
Drosperinone and Estradiol Tabs- 0,25 mg-0,5 mg(Generic of Angeliq) | LUPIN INDORE | INDORE OC | REGULAR | NA | NA | NA | 02 Apr 2015 | 21 May 2015 | NA | NA | 29 Jan 2015 | 30 Mar 2015 | 05 Apr 2015 | 22 Apr 2015 | NA | NA | NA | NA
DROSPIRENONE, ETHINYL ESTRADIOL 3MG, 3 MCG TAB | LUPIN INDORE | INDORE OC | NA | NA | NA | NA | 17 Mar 2014 | 17 Oct 2014 | NA | NA | 29 Jun 2014 | 18 Aug 2014 | 02 Aug 2014 | 10 Sep 2014 | 29 Jun 2014 | 18 Aug 2014 | NA | NA
Duloxetine DR Capsules | LUPIN TARAPUR | GOA | NA | NA | NA | NA | 01 Mar 2015 | 01 Feb 2015 | NA | NA | 07 Sep 2014 | 16 Dec 2014 | 27 Nov 2014 | 21 Jan 2015 | NA | NA | NA | NA
Eq of ActivellaR [E and NEA Tablets] | OUTSOURCED, LUPIN INDORE | INDORE OC | CRITICAL | N.V. ORGANON NEITHERLAND | NA | Activella | 01 Mar 2015 | 27 May 2015 | 10 Jan 2015 | 11 Mar 2015 | 26 Dec 2014 | 28 Mar 2015 | 17 Mar 2015 | 12 May 2015 | NA | NA | NA | NA
Eq of FemhrtR (NEA and EE Tablets) | OUTSOURCED, LUPIN INDORE | INDORE OC | CRITICAL | N.V. ORGANON | NA | Femhrt | 02 Apr 2015 | 21 May 2015 | NA | NA | 29 Jan 2015 | 30 Mar 2015 | 05 Apr 2015 | 22 Apr 2015 | NA | NA | NA | NA
Esomeprazole Magnesium DR Capsules | LUPIN DABASHA | GOA | REGULAR | NA | NA | Nexium | 23 Nov 2014 | 23 Nov 2014 | NA | NA | 20 May 2014 | 12 Sep 2014 | 09 Aug 2014 | 07 Nov 2014 | NA | NA | NA | NA
Estrostep FE (Norethindrone acetata , ethinyl estradiol , ferrous fumarate) | LUPIN INDORE | INDORE OC | CRITICAL | NA | NA | NA | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
FENOFIBRATE TABS | LUPIN TARAPUR | GOA | CRITICAL | NA | NA | NA | 01 Dec 2014 | 29 Jan 2015 | NA | NA | 26 Jun 2014 | 31 Oct 2014 | 04 Dec 2014 | 19 Jan 2015 | NA | NA | NA | NA
Flupirtine Cap | LUPIN DABASHA | INDORE OSD/OPTHAL | CRITICAL | NA | NA | Katadalon | 30 Sep 2014 | 11 Dec 2014 | NA | NA | 24 Sep 2014 | 25 Dec 2014 | 03 Oct 2014 | 03 Nov 2014 | NA | NA | NA | NA
GLICLAZIDE | OUTSOURCED | GOA | REGULAR | NA | NA | NA | 01 Jan 2015 | 01 Apr 2015 | 30 Oct 2014 | 29 Dec 2014 | NA | NA | 03 Jan 2015 | 18 Feb 2015 | NA | NA | NA | NA
GLICLAZIDE TAB_STADA | OUTSOURCED | GOA | REGULAR | BAL PHARMA | NA | Diamicron | 01 Dec 2013 | 10 Aug 2014 | 29 Sep 2013 | 28 Nov 2013 | NA | NA | 03 Jul 2014 | 29 Jul 2014 | NA | NA | NA | NA
Irbesartan tablets (Australia) | LUPIN TARAPUR | INDORE OSD/OPTHAL | REGULAR | NA | NA | Avapro | 02 Apr 2015 | 02 Apr 2015 | NA | NA | 06 Nov 2014 | 14 Feb 2015 | 26 Jan 2015 | 22 Mar 2015 | NA | NA | NA | NA
LAMIVUDINE TABS | OUTSOURCED | GOA | REGULAR | NA | NA | NA | 01 Nov 2014 | 30 Dec 2014 | 30 Aug 2014 | 29 Oct 2014 | NA | NA | 03 Nov 2014 | 19 Dec 2014 | NA | NA | NA | NA
Lamotrigine ER Tabs | OUTSOURCED | GOA | CRITICAL | CTX LIFE SCI. | NA | Lamictal XR | 01 Mar 2015 | 25 May 2015 | 28 Dec 2014 | 26 Feb 2015 | NA | NA | 03 Mar 2015 | 15 May 2015 | NA | NA | NA | NA
LANSOPRAZOLE | LUPIN TARAPUR | INDORE OSD/OPTHAL | CRITICAL | NA | NA | NA | 22 Apr 2015 | 22 Apr 2015 | NA | NA | 09 Dec 2014 | 14 Feb 2015 | 05 Feb 2015 | 12 Mar 2015 | NA | NA | NA | NA
Lansoprazole OD Tab (STADA-FRANCE) | LUPIN TARAPUR | INDORE OSD/OPTHAL | NA | NA | NA | NA | 01 Oct 2014 | 26 Dec 2014 | NA | NA | 02 Aug 2014 | 10 Nov 2014 | 22 Oct 2014 | 16 Dec 2014 | NA | NA | NA | NA
Lansoprazole ODT 15mg and 30mg | LUPIN TARAPUR | INDORE OSD/OPTHAL | REGULAR | NA | NA | Zoton Fastab | 01 Nov 2014 | 30 Jan 2015 | NA | NA | 09 Feb 2014 | 04 Jun 2014 | 19 Nov 2014 | 30 Dec 2014 | NA | NA | NA | NA
Levofloxacin (250 and 500mg tablet) | OUTSOURCED | GOA | CRITICAL | NA | NA | NA | 02 Apr 2015 | 20 Jun 2015 | NA | NA | 29 Jan 2015 | 30 Mar 2015 | 04 Apr 2015 | 20 May 2015 | NA | NA | NA | NA
Levonorgestrel 1,5MG Tab | LUPIN INDORE | INDORE OC | NA | NA | NA | NA | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
Levonorgestrel and Ethinyl estradiol tablets 0,15mg and 0,03 mg | LUPIN INDORE | INDORE OSD/OPTHAL | CRITICAL | NA | NA | NA | 02 Apr 2015 | 02 Apr 2015 | NA | NA | 06 Nov 2014 | 14 Feb 2015 | 26 Jan 2015 | 22 Mar 2015 | NA | NA | NA | NA
Levonorgestrel EE 0,1 mg and 0,02 mg | LUPIN INDORE | INDORE OSD/OPTHAL | CRITICAL | NA | NA | Miranova | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
Levonorgestrel,EE 0,125mg and 0,03mg (HORMOSAN) | LUPIN INDORE | INDORE OC | REGULAR | NA | Onarelle | Monostep | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
Lisinopril Tab | LUPIN MANDIDEEP | GOA | REGULAR | NA | NA | Zestril | 31 Aug 2014 | 01 Mar 2015 | NA | NA | 14 Jun 2014 | 14 Sep 2014 | 11 Dec 2014 | 21 Jan 2015 | NA | NA | NA | NA
Lo Loestrin FE (Norethindrone acetata , ethinyl estradiol , ferrous fumarate) | LUPIN INDORE | INDORE OC | REGULAR | NA | NA | Loestrin Fe 1/20 | 02 Apr 2015 | 02 Apr 2015 | NA | NA | 06 Nov 2014 | 14 Feb 2015 | 26 Jan 2015 | 22 Mar 2015 | NA | NA | NA | NA
Loestrin FE 1,5_30(Norethindrone acetata,ethinyl estradiol,ferrous fumarate) | LUPIN INDORE | INDORE OC | REGULAR | NA | NA | NA | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
Loestrin FE 1_20(Norethindrone acetata,ethinyl estradiol,ferrous fumarate) | LUPIN INDORE | INDORE OC | REGULAR | LUPIN INDORE | Loestrin Fe 1/20 | Loestrin Fe 1/20 | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
Lo-Ovral - Low-Ogestrel(Norgestrel , ethinyl estradiol) | LUPIN INDORE | INDORE OC | REGULAR | NA | NA | NA | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
Meclizine HCl Tabs | OUTSOURCED | GOA | REGULAR | SRI KRISHNA | NA | Antivert | 01 Nov 2014 | 29 Dec 2014 | 25 Aug 2014 | 24 Oct 2014 | NA | NA | 03 Nov 2014 | 19 Dec 2014 | NA | NA | NA | NA
Memantine HCl Tablets | LUPIN TARAPUR | GOA | REGULAR | NA | NA | Namenda | 02 Apr 2015 | 02 Apr 2015 | NA | NA | 06 Nov 2014 | 14 Feb 2015 | 26 Jan 2015 | 22 Mar 2015 | NA | NA | NA | NA
Memantine Tablets (ANTIBIOTICE, GLENMARK) |  |  |  | NA | NA | NA | 02 Apr 2015 | 02 Apr 2015 | NA | NA | 06 Nov 2014 | 14 Feb 2015 | 26 Jan 2015 | 22 Mar 2015 | NA | NA | NA | NA
Memantine Tablets-Hormo | LUPIN TARAPUR | GOA | CRITICAL | NA | NA | Ebixa | 03 Oct 2013 | 27 Oct 2014 | NA | NA | 13 Jul 2014 | 10 Aug 2014 | 15 Aug 2014 | 25 Sep 2014 | NA | NA | NA | NA
Memantine Tablets-UK | LUPIN TARAPUR | GOA | CRITICAL | NA | NA | Ebixa | 03 Oct 2013 | 27 Oct 2014 | NA | NA | 13 Jul 2014 | 10 Aug 2014 | 15 Aug 2014 | 25 Sep 2014 | NA | NA | NA | NA
Memantine Tabs | LUPIN TARAPUR | GOA | REGULAR | NA | NA | NA | 02 Apr 2015 | 02 Apr 2015 | NA | NA | 06 Nov 2014 | 14 Feb 2015 | 26 Jan 2015 | 22 Mar 2015 | NA | NA | NA | NA
Metoprolol Tartrate Tablets USP | OUTSOURCED | INDORE OSD/OPTHAL | REGULAR | IPCA LABS | NA | Generic Teva | 02 Apr 2015 | 20 Jun 2015 | NA | NA | 29 Jan 2015 | 30 Mar 2015 | 04 Apr 2015 | 20 May 2015 | NA | NA | NA | NA
Mircette(Desogestrel , Ethinyl Estradiol ) | LUPIN INDORE | INDORE OC | REGULAR | NA | NA | Mircette | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
Omeprazole Capsules | LUPIN TARAPUR | INDORE OSD/OPTHAL | REGULAR | NA | NA | Losec | 01 Oct 2014 | 23 Dec 2014 | NA | NA | 02 Dec 2012 | 08 Jan 2013 | 04 Oct 2014 | 09 Nov 2014 | NA | NA | NA | NA
Paroxetine HCl CR Tabs | OUTSOURCED | INDORE OSD/OPTHAL | REGULAR | MEDICHEM | NA | Paxil CR | 02 Apr 2015 | 20 Jun 2015 | NA | NA | 29 Jan 2015 | 30 Mar 2015 | 04 Apr 2015 | 20 May 2015 | NA | NA | NA | NA
Pioglitazone Tablets | OUTSOURCED | INDORE OSD/OPTHAL | CRITICAL | MSN ORGANICS PVT. LTD. | NA | Actos | 02 Apr 2015 | 02 Apr 2015 | 16 Nov 2014 | 15 Jan 2015 | NA | NA | 21 Jan 2015 | 17 Mar 2015 | NA | NA | NA | NA
Plan B Onestep (Fall Back Solo) (Levonorgestrel ) | LUPIN INDORE | INDORE OC | CRITICAL | NA | Fall back Solo | PlanB Onestep | 19 Jun 2014 | 09 Aug 2014 | NA | NA | 19 Apr 2014 | 20 Jul 2014 | 09 Jul 2014 | 26 Jul 2014 | NA | NA | NA | NA
Potassium Chloride ER Caps | OUTSOURCED | INDORE OSD/OPTHAL | CRITICAL | KLINGE CHEMICALS | NA | Micro-K & Micro-K10 | 02 Apr 2015 | 20 Jun 2015 | NA | NA | 29 Jan 2015 | 30 Mar 2015 | 04 Apr 2015 | 20 May 2015 | NA | NA | NA | NA
Pregabalin Caps | LUPIN DABASHA | GOA | CRITICAL | NA | NA | Lyrica | 01 Oct 2014 | 01 Jan 2015 | NA | NA | 02 Aug 2014 | 03 Oct 2014 | 17 Oct 2014 | 01 Dec 2014 | NA | NA | NA | NA
Pregabalin Oral Solution | LUPIN DABASHA | AURANGABAD | REGULAR | NA | NA | Lyrica | 01 Oct 2014 | 01 Jan 2015 | NA | NA | 04 Sep 2014 | 15 Nov 2014 | 27 Oct 2014 | 21 Dec 2014 | NA | NA | NA | NA
Propranolol HCL ER Caps | OUTSOURCED | INDORE OSD/OPTHAL | REGULAR | IPCA LABS | NA | Inderal LA | 02 Apr 2015 | 20 Jun 2015 | NA | NA | 29 Jan 2015 | 30 Mar 2015 | 04 Apr 2015 | 20 May 2015 | NA | NA | NA | NA
Quinine Sulfate Caps | OUTSOURCED | GOA | REGULAR | BUCHLER GMBH | NA | Qualaquin | 01 Sep 2014 | 17 Oct 2014 | 30 Jun 2014 | 29 Aug 2014 | NA | NA | 03 Sep 2014 | 07 Oct 2014 | NA | NA | NA | NA
Ramipril , HCTZ Tablets | LUPIN MANDIDEEP | GOA | REGULAR | NA | NA | Delix Plus | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
Ramipril Cap | LUPIN MANDIDEEP | GOA | NA | NA | NA | Ramiwin® Aventis | 31 Aug 2014 | 12 Nov 2014 | NA | NA | 14 Jun 2014 | 14 Sep 2014 | 12 Sep 2014 | 28 Oct 2014 | NA | NA | NA | NA
Risperidone |  |  |  | NA | NA | NA | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
Sevelamer Carbonate POS | LUPIN TARAPUR | GOA | REGULAR | NA | NA | Renvela | 01 Apr 2015 | 10 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 04 Apr 2015 | 25 Apr 2015 | NA | NA | NA | NA
Sevelamer Carbonate Tabs | LUPIN TARAPUR | GOA | REGULAR | NA | NA | NA | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
Telmisartan and HCTZ Tabs | OUTSOURCED | GOA | REGULAR | AMINO CHEMICALS | NA | Micardis HCT | 02 Apr 2015 | 02 Apr 2015 | 16 Nov 2014 | 15 Jan 2015 | NA | NA | 21 Jan 2015 | 17 Mar 2015 | NA | NA | NA | NA
Telmisartan Tablets | LUPIN TARAPUR | GOA | REGULAR | NA | NA | NA | 02 Apr 2015 | 02 Apr 2015 | NA | NA | 06 Nov 2014 | 14 Feb 2015 | 26 Jan 2015 | 22 Mar 2015 | NA | NA | NA | NA
TIANEPTINE TABLETS - MYLAN(FRANCE) | NA | GOA | CRITICAL | NA | NA | NA | 01 Aug 2014 | 15 Oct 2014 | 10 May 2014 | 08 Aug 2014 | NA | NA | 14 Aug 2014 | 28 Sep 2014 | NA | NA | NA | NA
Tianeptine Tablets-Mylan | OUTSOURCED | GOA | CRITICAL | QUIMICA | NA | Stablon | 02 Apr 2015 | 02 Apr 2015 | 16 Nov 2014 | 15 Jan 2015 | NA | NA | 21 Jan 2015 | 17 Mar 2015 | NA | NA | NA | NA
Tolterodine Tartrate ER Caps | LUPIN TARAPUR | INDORE OSD/OPTHAL | REGULAR | NA | NA | Detrol LA | 01 Sep 2014 | 02 Apr 2015 | NA | NA | 06 Nov 2014 | 14 Feb 2015 | 26 Jan 2015 | 22 Mar 2015 | NA | NA | NA | NA
Triphasil-Trivora (Generic)(Levonorgestrel , ethinyl estradiol) | LUPIN INDORE | INDORE OC | REGULAR | NA | NA | Trivora | 15 Aug 2014 | 05 Nov 2014 | NA | NA | 11 Jun 2014 | 16 Sep 2014 | 31 Aug 2014 | 21 Oct 2014 | NA | NA | NA | NA
Trospium Tab (ARISTO) | OUTSOURCED | INDORE OSD/OPTHAL | CRITICAL | PROCOS | NA | NA | 01 Dec 2014 | 03 Feb 2015 | 30 Aug 2014 | 28 Nov 2014 | NA | NA | 03 Dec 2014 | 18 Jan 2015 | NA | NA | NA | NA
Trospium Tab (Hormosan) | OUTSOURCED | INDORE OSD/OPTHAL | CRITICAL | PROCOS | NA | Spasmex | 01 Dec 2014 | 28 Feb 2015 | 29 Sep 2014 | 28 Nov 2014 | NA | NA | 03 Dec 2014 | 18 Jan 2015 | NA | NA | NA | NA
Valsartan and Amlodipine (80 and 5 mg tablet) | LUPIN TARAPUR | GOA | NA | NA | NA | NA | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
Valsartan Tabs | LUPIN TARAPUR | GOA | REGULAR | NA | NA | NA | 02 Apr 2015 | 21 May 2015 | NA | NA | 14 Jan 2015 | 16 Apr 2015 | 05 Apr 2015 | 07 Apr 2015 | NA | NA | NA | NA
Vancomycin Caps | OUTSOURCED | GOA | CRITICAL | ZHEJIANG | NA | Vancocin | 01 Nov 2014 | 14 Jan 2015 | 05 Jun 2013 | 20 Aug 2013 | NA | NA | 04 Nov 2014 | 04 Jan 2015 | NA | NA | NA | NA
Venlafaxine XL Cap | LUPIN DABASHA | GOA | CRITICAL | NA | Effexor | NA | 21 Dec 2012 | 01 Apr 2015 | NA | NA | 12 Oct 2014 | 20 Dec 2014 | 24 Nov 2014 | 02 Jan 2015 | NA | NA | NA | NA
Yaz (Nikki)(Drosperinone , EE ) | LUPIN INDORE | INDORE OC | CRITICAL | NA | NIKKI | Yaz | 02 Apr 2015 | 02 Apr 2015 | NA | NA | 06 Nov 2014 | 14 Feb 2015 | 26 Jan 2015 | 22 Mar 2015 | NA | NA | NA | NA